## Scenario Library
ID | Example Set | Company | Scenario | Critical Level | Affected Function | RTO | RPO | Financial Impact | Threat | Likelihood | Severity | Recovery Strategy | DR Plan | Roles & Responsibilities | Alternate Site | Communication Plan | Incident Response Steps | Testing | Maintenance | AWS Services
A | Set 1 – E-Commerce (ShopNow) | ShopNow | Office Wi-Fi Outage | Low | Internal staff communication | 4 hours | N/A | Minimal | ISP failure or router hardware fault | High | Low | Staff switch to mobile hotspots or WFH; IT contacts ISP | No IT failover; backup 4G routers on-site | IT Helpdesk: diagnose & escalate; Team leads: notify WFH | Staff work remotely via VPN | IT sends Slack/email to all staff within 15 min | Detect → check router → contact ISP → activate backup router | Annual drill: simulate ISP outage, verify backup router | Review ISP SLA annually; update router firmware quarterly | N/A
B | Set 1 – E-Commerce (ShopNow) | ShopNow | Key Supplier Shipment Delay | Medium | Order fulfillment, customer delivery | 48 hours | N/A | ~$200K/day | Supplier bankruptcy, port strike, natural disaster | Medium | Medium | Activate secondary supplier; prioritize high-value orders; notify customers | Update inventory/OMS with new supplier lead times | Procurement Mgr: contact secondary supplier in 4h; Ops Mgr: re-prioritize queue | Secondary warehouse if primary fulfillment center affected | Internal: Ops team in 2h; External: customers in 24h | Detect delay → escalate to Ops Mgr → activate secondary supplier → update ETA | Semi-annual tabletop: simulate supplier failure | Review supplier contracts & secondary supplier list every 6 months | N/A
C | Set 1 – E-Commerce (ShopNow) | ShopNow | Ransomware Attack on Production DB | High | Entire platform (orders, payments, customer data) | 4 hours | 1 hour | $5,600/min + regulatory fines + reputational damage | Ransomware via phishing or unpatched vulnerability | Medium | Critical | Isolate infected systems; restore from clean backup; failover to AWS DR; engage IR firm | Hot standby multi-region (ap-southeast-1 → ap-east-1); hourly RDS/S3 snapshots; Route 53 auto-failover in 5 min; 30-day retention | CISO: lead response; DR Lead: execute runbook; Legal: GDPR notification; CEO: comms approval | Hot standby AWS region — full platform in 4h | Internal: 30 min; Customers: status page 1h; Regulators: 72h (GDPR); Media: post legal review | GuardDuty alert → isolate → failover → forensics → patch → failback → post-incident report | Quarterly tabletop; bi-annual full DR drill; annual pen test | Critical patches in 24h; weekly backup restore test; BCP review after each incident | RDS, S3, Route 53, GuardDuty, AWS Backup
D | Set 2 – AWS Cloud (CloudBiz) | CloudBiz | AWS Lambda Throttling | Low | Background jobs (reports, email notifications) | 1 hour | N/A | Minimal – jobs queued | Traffic spike exceeds Lambda concurrency limit (default 1,000) | Medium | Low | SQS absorbs excess requests; request concurrency limit increase via Service Quotas | Lambda + SQS DLQ; CloudWatch alarm → SNS; reserved concurrency for critical functions | On-call Engineer: acknowledge alarm, review metrics; Platform Lead: submit quota increase | N/A – SQS buffers all requests | CloudWatch → SNS → PagerDuty → on-call engineer; no customer comms unless SLA breached | CloudWatch detects throttle → SNS alert → engineer reviews → increase concurrency → monitor backlog | Quarterly load test to simulate throttling; verify DLQ alerts | Review concurrency limits monthly; set CloudWatch alarm at 80% threshold | Lambda, SQS, CloudWatch, SNS, Service Quotas
E | Set 2 – AWS Cloud (CloudBiz) | CloudBiz | Single Availability Zone (AZ) Outage | Medium | Web application, API, database | 15 minutes | Near-zero | ~$84K/hour | AWS AZ-level hardware or power failure | Low | Medium | Multi-AZ architecture absorbs failure automatically; ALB re-routes; RDS promotes standby | Multi-AZ warm standby; EC2 ASG spans 3 AZs; RDS Multi-AZ failover in 60–120s; ALB health checks deregister in 30s; EFS/S3 AZ-resilient | On-call Engineer: monitor AWS Health + CloudWatch; Platform Lead: confirm recovery | Remaining AZs in same region serve all traffic automatically | Internal: AWS Health + PagerDuty; External: status page if >5 min degradation | AWS Health alert → CloudWatch alarms → ALB re-routes → RDS failover → ASG replaces instances → confirm recovery | Semi-annual chaos test via AWS Fault Injection Simulator; verify RDS failover time | Ensure ASG spans min 2 AZs; review RDS Multi-AZ after infra changes; monthly Health Dashboard review | EC2, RDS Multi-AZ, ALB, Auto Scaling, EFS, S3, AWS Health, CloudWatch
F | Set 2 – AWS Cloud (CloudBiz) | CloudBiz | Full AWS Region Outage | High | Entire SaaS platform – all services unavailable | 1 hour | 15 minutes | $5,600/min + SLA breach penalties + customer churn | Large-scale AWS region failure (e.g., ap-southeast-1 power/network event) | Very Low | Critical | Pre-provisioned warm standby in ap-northeast-1; DNS failover via Route 53; continuous data replication | Warm standby cross-region; Aurora Global DB (lag <1s); S3 CRR; DynamoDB Global Tables; ASG pre-warmed at 20% → scales to 100%; Route 53 failover in 60s; CloudFront unaffected; gradual failback via weighted routing | CTO: declare DR event; DR Lead: execute runbook; DB Lead: promote Aurora Global; DevOps Lead: scale ASG; Comms Lead: customer updates | Warm standby in ap-northeast-1 (Tokyo) – full capacity in 30 min | Internal: PagerDuty war room in 10 min; Customers: status page 15 min / email 30 min; Enterprise: account mgr calls 30 min; Regulators: if data residency SLA affected | Health Dashboard → Route 53 failover → CTO declares DR → promote Aurora → scale ASG → confirm healthy → notify customers → monitor → failback via weighted routing → post-incident report | Quarterly tabletop; bi-annual full region failover drill (FIS); annual DR audit | Weekly Aurora replication lag review; monthly S3 CRR metrics; update runbook after infra changes; quarterly Route 53 health check review | Route 53, Aurora Global, S3 CRR, DynamoDB Global Tables, EC2 ASG, CloudFront, AWS Fault Injection Simulator

## BCP Components
# | Phase | Component | Description | Key Data Point | Source
1 | 1 – Understand | Business Impact Analysis | Identifies critical functions; defines RTO & RPO | 60% of companies losing data shut down within 6 months | Boston Computing Network
2 | 1 – Understand | Risk Assessment | Identifies threats; evaluates likelihood & severity | 95% of breaches caused by human error | IBM Security Report
3 | 2 – Prepare | Recovery Strategies | Plans to restore critical functions within RTO/RPO | 2.5x more likely to close without a recovery strategy | FEMA
4 | 2 – Prepare | DR Plan & Strategy | IT-focused: failover, backup, restore, failback | 93% of companies without DR close within 1 year of major data disaster | University of Texas
5 | 2 – Prepare | Roles & Responsibilities | BCP/DR team structure; clear ownership per task | — | ISO 22301
6 | 2 – Prepare | Alternate Site / Work Arrangements | Hot/Warm/Cold standby; remote work capability | — | NIST SP 800-34
7 | 2 – Prepare | Communication Plan | Internal & external notifications; contact lists | Poor comms increases recovery time by up to 50% | Deloitte Crisis Management Survey
8 | 3 – Respond | Incident Response Plan | Immediate actions; escalation; decision authority | IR team saves avg $2.66M per breach | IBM Cost of a Data Breach 2023
9 | 4 – Sustain | Testing & Exercises | Tabletop, simulation, full DR drills | Only 23% of orgs test BCP annually | Disaster Recovery Journal
10 | 4 – Sustain | Plan Maintenance | Scheduled reviews; version control; change mgmt | Regular testers recover 2x faster | IBM

## DR Strategy Matrix
Strategy | RTO | RPO | Relative Cost | Best For | AWS Implementation | Scenario
Backup & Restore | Hours | Hours | $ (Lowest) | Non-critical, cold data, archival | S3 + AWS Backup + Glacier; restore EC2 from AMI | D
Pilot Light | 30–60 min | Minutes | $$ (Low) | Core services; minimal always-on infra | Minimal EC2/RDS running; scale up on event via ASG + Route 53 | —
Warm Standby | 15–30 min | Seconds–Minutes | $$$ (Medium) | Business-critical SaaS; balanced cost/RTO | Scaled-down ASG in DR region; Aurora Global; S3 CRR; Route 53 failover | E, F
Multi-Site Active/Active | Near-zero | Near-zero | $$$$ (Highest) | Mission-critical; financial; zero tolerance | Multi-region ALB + Global Accelerator; DynamoDB Global Tables; Aurora Global active/active | —